## README
Foolproof Study Plan — Project Tracker
Project | Parametric Study of Regeneration Process of CO₂ Capture Sorbent in Packed-Bed Columns
Student | Year 3 ES (N93), Ngee Ann Polytechnic
Institution supervisors | Prof. Prapatsorn Borisut; Prof. Erik Birgersson
NP supervisor | Dr. Pham the Hanh
Semester | April 2026
Plan issued | 2026-04-20
Total assessment | 100% (Journals 10% + Interim 10% + Interim Assess 30% + Final 10% + Final Assess 30% + Panel 10%)
Tabs in this workbook
1. Master Schedule | 18-week Gantt-style plan aligned exactly to the NP April-2026 timeline.
2. Deliverables | All assessed items with due dates, weights and status flags.
3. Bi-weekly Journal | Four pre-prepared journal templates (Wk 3, 5, 13, 15).
4. Experiment Log | 39 planned simulation runs with baseline, OAT sweeps and T×Q interaction.
5. Hypotheses | H1–H5 with accept/refine thresholds, linked to sub-topics.
6. Risk Register | 9 named risks with triggers and responses.
7. Reading Tracker | Tier-1/2/3 reading list with progress field.
8. Meeting Log | Template to record supervisor meetings, decisions and action items.
9. Garntt Chart
10. References

## 1. Master Schedule
Master Schedule — 18 Weeks (aligned to NP April 2026 Semester)
Wk | Dates | Phase | Math / Theory (M) | Technical (T) | Writing (W) | Deliverable / Gate | Status
1 | 20–24 Apr | P0 Kickoff | Evans §3.1–3.2 (linear first-order PDE, characteristics) | Install Python stack; clone heat-eq template; read all 7 research.md sources | Charter + LaTeX skeleton; parameter-table from Elfving/Bos | Wk-1 briefing + 1st joint meeting
2 | 27 Apr–1 May | P1 Derivation | Evans §3.4 / LeVeque Ch 3 (Rankine–Hugoniot, entropy) | Derive 4-PDE system by hand from CV balance | Derivation subsection (Interim §3 seed)
3 | 4–8 May | P1 Non-dim | Buckingham Π; scaling | Non-dim all 4 PDEs; identify Pe, NTU, Λ, α, Bi_w | Dimensionless-analysis subsection | DELIV: Journal #1 — Mon 4 May
4 | 11–15 May | P2 Linear solver | Method of lines; stiff ODE; BDF2/LSODA | Code heat-eq MOL; validate vs analytical Gaussian | Validation figure #1 draft | GATE A: error < 1%
5 | 18–22 May | P2 Coupled solver | LDF kinetics; upwind ≡ entropy numerically | Add Langmuir + LDF; zero-heat sanity check | Numerical-methods chapter draft | DELIV: Journal #2 — Mon 18 May
6 | 25–29 May | P2 Benchmark + Interim draft | Heat-of-ads feedback in v_th | Elfving baseline; compute v_th, SER, Δq | Interim Report full draft (~3000 w) | GATE B (R–H ±15%) + GATE C (SER ±20%)
7 | 1–5 Jun | Interim Gate | — | Patch any gaps flagged at review | Submit Interim; 10-min slides | DELIV: Interim Report Mon 1 Jun; Review Wk 7–8
8 | 8–12 Jun | P3 Sensitivity Part 1 | Sensitivity equations (∂T/∂θ PDE) | OAT sweep: T_regen (5 lvls) + Q_purge (3 lvls) | Running Results log
9 | 15–19 Jun | TERM BREAK | Optional: LeVeque / Villani for pleasure | — | — | No hard deliverable
10 | 22–28 Jun | TERM BREAK | Rest; don't burn out | — | — | No hard deliverable
11 | 29 Jun–3 Jul | P3 Sensitivity Part 2 | Local equilibrium limit; NTU → ∞ | OAT: L (3 lvls) + m (3 lvls); extract v_th, τ_90, T_peak | Results log
12 | 6–10 Jul | P4 Energy analysis | Drechsler–Agar energy decomposition | Post-process SER = Q_sens + Q_des + Q_parasitic | Energy subsection
13 | 13–17 Jul | P4 Interaction | Response-surface methodology (quadratic) | T × Q 5×3 grid (15 runs); fit surface | Interaction Results | DELIV: Journal #3 — Mon 13 Jul
14 | 20–24 Jul | P5 Dimensionless recast | Rescale in (Pe, NTU, Λ); log-sensitivity ranking | Universal plots; parameter ranking | Discussion draft
15 | 27–31 Jul | P6 Writing Sprint 1 | — | Code cleanup; all figures 300 dpi | Final Report v0.5 — to both supervisors | DELIV: Journal #4 — Mon 27 Jul
16 | 3–7 Aug | P6 Writing Sprint 2 | — | Any requested reruns | Final Report v1.0 — proofread, formatted
17 | 10–14 Aug | P7 Submit + prep | — | — | Submit Mon 10 Aug; build slides; 2 rehearsals | DELIV: Final Report Mon 10 Aug
18 | 17–19 Aug | P7 Defence | — | — | Slide revisions after dry-run | DELIV: Final Presentation + panel

## 2. Deliverables
Deliverables — Assessed Items
Wk | Deliverable | Due date | Weight | Assessor | Status | Notes
3 | Bi-weekly Journal #1 | 2026-05-04 | 2.5% | NP supervisor | Not started
5 | Bi-weekly Journal #2 | 2026-05-18 | 2.5% | NP supervisor | Not started
7 | Interim Report | 2026-06-01 | 10% | NP + Institution | Not started | Hard gate
7 | Interim Assessment (Institution) | 2026-06-05 | 20% | Prof. Borisut / Prof. Birgersson | Not started | Filled during Wk 7–8
7 | Interim Assessment (NP) | 2026-06-05 | 10% | NP supervisor | Not started | Filled during Wk 7–8
13 | Bi-weekly Journal #3 | 2026-07-13 | 2.5% | NP supervisor | Not started
15 | Bi-weekly Journal #4 | 2026-07-27 | 2.5% | NP supervisor | Not started
17 | Final Report | 2026-08-10 | 10% | NP + Institution | Not started | 6k–8k words
18 | Final Assessment (Institution) | 2026-08-19 | 20% | Prof. Borisut / Prof. Birgersson | Not started
18 | Final Assessment (NP) | 2026-08-19 | 10% | NP supervisor | Not started
18 | Final Presentation (Panel) | 2026-08-19 | 10% | Panel (NP + other supervisors) | Not started | 20–25 min + Q&A
| TOTAL |  | 100%

## 3. Bi-weekly Journal
Bi-weekly Journal Templates (Journals #1–#4)
Section | Prompt | Entry
JOURNAL #1 — Wk 3, due Mon 4 May 2026
1. What I did | Methods of characteristics exercises; 4-PDE derivation; Π-group identification; dev environment set up. | Read up on conversation math (conservationdissipation.pdf) Created study plan for upcoming semester for ProjID3, derived equations of Change for Pure Fluids in Terms of the Fluxes
2. What I learned | The mathematical insight of the week — e.g., why upwind differencing is the numerical analogue of the entropy condition.
3. Blockers / questions | e.g., 'Need Langmuir q_m0, b_0, ΔH_ads from Prof. Borisut by end of Wk 2 else will use Elfving defaults.'
4. Plan for next 2 weeks | Match Part III of master plan: code linear solver (Wk 4); extend to coupled (Wk 5).
JOURNAL #2 — Wk 5, due Mon 18 May 2026
1. What I did | Gate A passed; nonlinear LDF + Langmuir coupled; first breakthrough curve; v_th hand-computed.
2. What I learned | How the chord vs tangent of the isotherm sets shock velocity.
3. Blockers / questions
4. Plan for next 2 weeks | Gate B + C; Elfving benchmark; draft Interim.
JOURNAL #3 — Wk 13, due Mon 13 Jul 2026
1. What I did | OAT for T_regen, Q_purge complete; H1 and H2 directions confirmed.
2. What I learned | Sensitivity magnitudes in log-space; where the SER(Q_purge) minimum actually sits.
3. Blockers / questions
4. Plan for next 2 weeks | L, m sweeps; T×Q interaction; energy analysis.
JOURNAL #4 — Wk 15, due Mon 27 Jul 2026
1. What I did | Dimensionless recast; response surface fitted; Final Report v0.5 circulated.
2. What I learned | Universal plots in (Pe, NTU) space — what transfers, what doesn't.
3. Blockers / questions
4. Plan for next 2 weeks | Address supervisor feedback; v1.0; final figures; rehearsals.

## 4. Experiment Log
Simulation / Experiment Log — 39 planned runs
Run ID | Phase | Sweep | T_regen (°C) | Q_purge (mL/min) | L (cm) | m (g) | Planned Wk | Status | v_th (m/s) | τ_90 (s) | SER (MJ/kg)
R00 | Validation | Baseline | 100 | 100 | 15 | 20 | 6 | Planned
R01-1 | OAT | T_regen | 60 | 100 | 15 | 20 | 8 | Planned
R01-2 | OAT | T_regen | 80 | 100 | 15 | 20 | 8 | Planned
R01-3 | OAT | T_regen | 100 | 100 | 15 | 20 | 8 | Planned
R01-4 | OAT | T_regen | 120 | 100 | 15 | 20 | 8 | Planned
R01-5 | OAT | T_regen | 150 | 100 | 15 | 20 | 8 | Planned
R02-1 | OAT | Q_purge | 100 | 40 | 15 | 20 | 8 | Planned
R02-2 | OAT | Q_purge | 100 | 100 | 15 | 20 | 8 | Planned
R02-3 | OAT | Q_purge | 100 | 500 | 15 | 20 | 8 | Planned
R03-1 | OAT | L | 100 | 100 | 7.5 | 20 | 11 | Planned
R03-2 | OAT | L | 100 | 100 | 15 | 20 | 11 | Planned
R03-3 | OAT | L | 100 | 100 | 30 | 20 | 11 | Planned
R04-1 | OAT | m_sorbent | 100 | 100 | 15 | 10 | 11 | Planned
R04-2 | OAT | m_sorbent | 100 | 100 | 15 | 20 | 11 | Planned
R04-3 | OAT | m_sorbent | 100 | 100 | 15 | 50 | 11 | Planned
R05-01 | Interaction | T × Q | 60 | 40 | 15 | 20 | 13 | Planned
R05-02 | Interaction | T × Q | 60 | 100 | 15 | 20 | 13 | Planned
R05-03 | Interaction | T × Q | 60 | 500 | 15 | 20 | 13 | Planned
R05-04 | Interaction | T × Q | 80 | 40 | 15 | 20 | 13 | Planned
R05-05 | Interaction | T × Q | 80 | 100 | 15 | 20 | 13 | Planned
R05-06 | Interaction | T × Q | 80 | 500 | 15 | 20 | 13 | Planned
R05-07 | Interaction | T × Q | 100 | 40 | 15 | 20 | 13 | Planned
R05-08 | Interaction | T × Q | 100 | 100 | 15 | 20 | 13 | Planned
R05-09 | Interaction | T × Q | 100 | 500 | 15 | 20 | 13 | Planned
R05-10 | Interaction | T × Q | 120 | 40 | 15 | 20 | 13 | Planned
R05-11 | Interaction | T × Q | 120 | 100 | 15 | 20 | 13 | Planned
R05-12 | Interaction | T × Q | 120 | 500 | 15 | 20 | 13 | Planned
R05-13 | Interaction | T × Q | 150 | 40 | 15 | 20 | 13 | Planned
R05-14 | Interaction | T × Q | 150 | 100 | 15 | 20 | 13 | Planned
R05-15 | Interaction | T × Q | 150 | 500 | 15 | 20 | 13 | Planned
R06-01 | Validation/diag | Gate A linear | 100 | 100 | 15 | 20 | 4 | Planned
R06-02 | Validation/diag | Gate B iso-Langmuir | 100 | 100 | 15 | 20 | 4 | Planned
R06-03 | Validation/diag | Gate C Elfving-60 | 100 | 100 | 15 | 20 | 4 | Planned
R06-04 | Validation/diag | CFL check | 100 | 100 | 15 | 20 | 4 | Planned
R06-05 | Validation/diag | Mass-bal check | 100 | 100 | 15 | 20 | 4 | Planned
R06-06 | Validation/diag | Energy-bal check | 100 | 100 | 15 | 20 | 4 | Planned
R06-07 | Validation/diag | Grid refine x2 | 100 | 100 | 15 | 20 | 4 | Planned
R06-08 | Validation/diag | dt refine x2 | 100 | 100 | 15 | 20 | 4 | Planned
R06-09 | Validation/diag | Rerun buffer | 100 | 100 | 15 | 20 | 4 | Planned
R06-10 | Validation/diag | Rerun buffer | 100 | 100 | 15 | 20 | 4 | Planned
Count | 40

## 5. Hypotheses
Hypotheses H1–H5 and Accept/Refine Thresholds
H# | Sub-topic | Hypothesis | Anchor source | Accept threshold | Verdict
H1 | Regeneration temperature | Raising T_regen 60→120 °C more than doubles initial desorption rate; Δcapacity ≥ 20%. Diminishing returns above ~120 °C. | Bos 2018; Serna-Guerrero 2010 | Rate ratio > 2.0 AND Δcapacity > 20% | Pending
H2 | Purge gas flow rate | SER vs Q_purge has an interior minimum in 100–500 mL/min range at fixed T. | Elfving 2021 | Local min exists in SER(Q) curve | Pending
H3 | Bed height (L) | v_front independent of L; t_BT linear in L; MTZ width ~ L^(1/2) / Pe. | Hanh 2024; Zanco 2022 | ¦slope v(L)¦/mean < 5%; R² of t_BT linear fit > 0.95 | Pending
H4 | Sorbent mass (m) | Q_sens linear in m; SER(m) has an interior optimum. | Zanco 2022; Drechsler 2020 | Linear Q_sens R² > 0.98; interior SER minimum observed | Pending
H5 | Axial T profile (Rankine–Hugoniot) | Simulated thermal-front velocity matches R–H prediction within ±15%. | Marx 2016; Zanco 2022 | ¦v_sim − v_RH¦/v_RH < 0.15 | Pending

## 6. Risk Register
Risk Register — 9 Named Risks
# | Risk | Likelihood | Impact | Trigger | Response | Status
R1 | Solver fails Gate A by end of Wk 4 | Medium | High | L² err > 1% or solver diverges | Fallback to Crank–Nicolson hand-coded; consult Birgersson; 3-day buffer | Open
R2 | SUTD does not supply sorbent / rig parameters by Wk 2 | Medium | High | No email reply end of Wk 2 | Use Elfving 2021 defaults as placeholders; document; escalate to NP supervisor | Open
R3 | Derivation chapter overrun → Interim late | Medium | Critical | Wk 6 Fri and Interim draft < 1500 w | Tighten scope: cover only H1, H2 in Interim; finish the rest by Wk 13 | Open
R4 | Stiff integrator collapses near pinch points | Low | Medium | Step size → 0; `LSODA` complains | Regularise isotherm; tune atol/rtol; try BDF | Open
R5 | Scope creep (2-D / Bayesian / experimental) | High | Medium | You find yourself reading Villani on a Wed morning | Part I §1.3 'Out of scope'. Bookmark for FYP. | Open
R6 | Burnout Wk 11–13 after break | Medium | Medium | Journal #3 late or thin; > 12 h weekends | Drop interaction grid 5×3 → 4×3; call NP supervisor | Open
R7 | Laptop / data loss | Low | Catastrophic | — | Nightly git push; weekly Drive backup of .ipynb + .npz | Open
R8 | Panel presentation overruns | Medium | Medium | Dry-run > 22 min | Two rehearsals; record once; open with the PHYSICAL picture, not equations | Open
R9 | Supervisor expectations diverge (SUTD vs NP) | Low | High | A supervisor is surprised by project direction in Wk 7 | Monthly 1-page joint status email (template in plan §IX) | Open

## 7. Reading Tracker
Reading Tracker (Tier 1 / 2 / 3)
Tier | Reference | Topic | Target week(s) | Status
1 | Evans, PDE, Ch 3 | Characteristics, shocks | Wk 1–2 | Not started
1 | LeVeque, Numerical Methods for Conservation Laws, Ch 3, 6–7 | Upwind, CFL | Wk 4–5 | Not started
1 | Ruthven, Principles of Adsorption, Ch 6, 8 | Packed-bed models | Wk 2–6 | Not started
1 | Elfving et al. 2021, Chem Eng J 404, 126337 | Primary benchmark | Wk 1, 6 | Not started
1 | Bos et al. 2018, I&EC Res 57, 11141 | Regeneration options | Wk 1, 8 | Not started
2 | Serna-Guerrero et al. 2010, CES 65, 4166 | Factorial DOE direction | Wk 8 | Not started
2 | Marx et al. 2016, I&EC Res 55, 1401 | 1-D non-isothermal calib. | Wk 6, 14 | Not started
2 | Zanco et al. 2022, Chem Eng J 430, 131000 | Axial T profile template | Wk 11 | Not started
2 | Hanh et al. 2024, J Taiwan IChE 164, 105681 | MTZ / ABU / AER | Wk 11, 14 | Not started
2 | Drechsler & Agar 2020, I&EC Res 59, 9207 | Energy decomposition | Wk 12 | Not started
2 | Bird/Stewart/Lightfoot, Transport Phenomena, Ch 6, 11, 14 | CV balances | Wk 2–3 | Not started
3 | Villani, Topics in Optimal Transport, Ch 1 | Multi-marginal link | Break | Optional
3 | Evans, PDE, Ch 5 | Sobolev spaces (enrichment) | Break | Optional
3 | Sources_csv.xlsx math papers (Laplacians; Multi-Marginal; Stat Mech) | Library math enrichment | Rolling | Optional

## 8. Meeting Log
Meeting Log — Supervisor Meetings
Date | Attendees | Topics discussed | Decisions | Action items | Owner / due
2026-04-22 | Student, NP supv, SUTD supv (Borisut + Birgersson) | Week-1 kick-off — scope, supervisor expectations, rig geometry, sorbent parameters |  | Obtain q_m0, b_0, ΔH_ads, d_c, L, ρ_p, ε, d_p | Student / end Wk 2

## 9. Gantt Chart
Phase | Task | Project Weeks
|  | April |  | May |  |  |  | June |  |  |  | July |  |  |  | August
|  | W0 (20/04) | W1 (27/04) | W2 (04/05) | W3 (11/05) | W4 (18/05) | W5 (25/05) | W6 (01/06) | W7 (08/06) | W8 (15/06) | W9 (22/06) | W10 (29/06) | W11 (06/07) | W12 (13/07) | W13 (20/07) | W14 (27/07) | W15 (03/08) | W16 (10/08) | W17 (17/08)
DELIVERABLES | first meetings with supervisors
Bi-weekly journal #1
Bi-weekly journal #2
Interim report
Interim review & presentation
Bi-weekly journal #3
Bi-weekly journal #4
Final report
Final presentation
P0 Kickoff | Learn firstorder quasilinear PDE
Learn method of characteristics
Install python
Read all sources in research.md
Set-up Latex skeleton
Week 1 briefing preparation

## 10. References
| References | Links | PDF | Progress | Description | References | Links | PDF | Progress | Description
Scope | CO2 Properties | Link to info |  |  |  | Optimizing amine-based adsorbents for direct air capture: A comprehensive review of performance under diverse climatic conditions | Link to info
| Understanding Molecular Algos | Link to info |  |  |  | On Comparing Packed Beds and Monoliths for CO2 Capture from Air Through Experiments, Theory, and Modelin | Link to info
| CO2 Alumina Adsorbent Simulation and Modelling | Link to info |  |  |  | Optimization of direct air capture processes using reactive transport models of adsorption-desorption cycle | Link to info
| Adsorbate Solid Monte Carlo Simulation | Link to info |  |  |  | Numerical study on a structured packed adsorption bed for indoor direct air capture | Link to info
| CO2 Capture Fixed Bed Coconut Shell | Link to info |  |  |  | Mass transfer from a fluid flowing through a porous media | Link to info
| CO2 & GHG Emissions (2020) | Link to info |  |  |  | A comprehensive review on direct air carbon capture (DAC) technology by adsorption: From fundamentals to applications | Link to info
| Micropore size distribution Monte Carlo | Link to info |  |  |  | Techno-economic analysis of packed bed and structured adsorbent for direct air capture | Link to info
| CO2 Sodium Hydroxide Absorption | Link to info |  |  |  |  | Link to info
| Equilibrium Kinetics of CO2 Absorption | Link to info |  |  |  |  | Link to info
| Mathematical Methods for Determining CO2 Absorption | Link to info |  |  |  |  | Link to info
| Efficient Synthesis of 2D Mica Nanosheets | Link to info | pdf |  |  |  | Link to info
| Sorbent in microextraction by packed sorbent | Link to info |  |  |  |  | Link to info
| Kinetic Diffusion Parameters CO 2 Sorbent | Link to info |  |  |  |  | Link to info
Maths | Nonlinear systems coupled through multi-marginal transport problems | Link to info | pdf |  |  |  | Link to info
| Spatial Dependent Nonlinear Fluid Transport Framework | Link to info |  |  |  |  | Link to info
| Reducing Nonlinear Transport Equations to Lapalcians | Link to info | pdf |  |  |  | Link to info
| Numerical Modelling Nonlinear Transport Adsorption | Link to info |  |  |  |  | Link to info
| Nonlinear Transport Equations from Statistical Mechanics | Link to info |  |  |  |  | Link to info
Link to info
Books | Introduction to Fluid Dynamics | Link to info |  | reading.. |  |  | Link to info
| Fluid Mechanics | Link to info |  |  |  |  | Link to info
Link to info
Papers | Fixed-bed column adsorption of carbon dioxide | Link to info | pdf |  |  |  | Link to info
| Enhancing CO2 Adsorption via Amine Impregnated Activated Carbon | Link to info | pdf |  |  |  | Link to info
| Methanol Production via CO2 Hydrogenation | Link to info | pdf |  |  |  | Link to info
Link to info
Links | Drive |  |  |  | Drive |  | Link to info
| Sutd library |  |  |  | Sutd library |  | Link to info