RESEARCH ROADMAP

Literature Review & Study Companion

Mathematical Modelling of a 1-D Axial, Non-Isothermal

CO₂ Adsorption Breakthrough Process in a Packed-Bed Column

| Prepared for | Loh John Ray — Year 3, Diploma in Engineering Science (N93), Ngee Ann Polytechnic |
| --- | --- |
| Institution supervisors | Prof. Parapsorb Borisut (sorbent chemistry) · Prof. Erik Birgersson (transport modelling) |
| Project | ES Design Project (4 credits), April 2026 semester |
| Roadmap version | v1.0 — prepared 1 July 2026, aligned to Study Plan v2.0 (rev. 30 Apr 2026) |
| Key gates | Interim Report — Mon 1 Jun 2026 (Wk 7) · Final Report — Mon 10 Aug 2026 (Wk 17) · Panel — 17–19 Aug 2026 (Wk 18) |

“You are here: Week 11 — Sensitivity Sweep, Part 2”

# Table of Contents

(If the list below appears empty, click into it and press Ctrl+A then F9 to refresh — a one-time Word quirk on first open.)

# Color Key — Study Types

Every activity in this roadmap is tagged by the same study-type legend used in the underlying Study Plan, so a glance at any table tells you what kind of effort a week or a task demands.

| Tag | Category | What it covers |
| --- | --- | --- |
| M | Math & Theory | Derivations, worked problems, canonical readings (Evans, LeVeque, Myers & Font). |
| T | Technical / Coding | Solver implementation, validation gates, simulation sweeps. |
| W | Writing | Report drafting, journal entries, figure preparation. |
| L | Literature | Papers and texts to read, annotate, and cite. |
| D/G | Deliverable / Gate | Hard due dates and technical pass/fail checkpoints — non-negotiable. |

# How to Use This Roadmap

This roadmap reorganises the Foolproof Study Plan into a working tool for the literature-review phase and beyond. It is deliberately redundant in two directions: the project-management spine (deadlines, gates, deliverables) keeps the degree assessment foolproof, and the literature + math spine keeps the science honest.

## Three ground rules

- Every Sunday evening, read the relevant week in the 18-Week Timeline before the week begins. Write Monday's journal entry first thing, not last thing.

- Bi-weekly journals are effectively free marks — missing one is the single most common way design projects lose a grade band.

- The Interim Report (Week 7) is a gate, not a preview: by then you need a derived PDE system, a validated solver, and baseline results matched to the Stampi-Bombelli 2024 benchmark.

## Using the note spaces

- Each paper in the Literature Anchor Map has a reading log: fill in the key result/equation, why it matters to your model, and any open question the moment you finish reading — not weeks later from memory.

- Tick the checkboxes as you go. A half-read paper with a ticked 'Key equations extracted' box is a flag to revisit before citing it.

- Use the blank Working Notes pages at the back for derivations that don't fit neatly under a single paper (e.g. combining Toth isotherm algebra with the R-H shock condition).

# Project Snapshot

## Problem statement

CO₂ capture by solid sorbents in packed-bed columns depends on how the mass-transfer zone (MTZ) propagates through the bed, when outlet concentration exceeds threshold, and how u, C_in, L, and T_ads jointly determine breakthrough time τ_BT and capacity utilisation η. This project derives the coupled 1-D breakthrough PDE system from first principles, validates a Method-of-Lines solver against traveling-wave theory and the Stampi-Bombelli (2024) benchmark, runs systematic OAT and interaction sweeps, and recasts results in (Pe, NTU) space.

## Objectives

| # | Objective | Evidence |
| --- | --- | --- |
| O1 | Derive the coupled mass-energy PDE system (Toth isotherm + LDF kinetics) from first-principles conservation laws. | Full derivation in Final Report Ch. 3 |
| O2 | Implement and validate the MOL solver against (a) analytical step response, (b) R-H shock velocity, (c) Stampi-Bombelli breakthrough curve. | Gates A/B/C — see Validation Gates section |
| O3 | Complete OAT sweep (u, C_in, L, T_ads × 3 levels) + u×C_in interaction grid. | ~39 simulations total |
| O4 | Recast sensitivity results in (Pe, NTU, α) space. | Response surface + Pareto ranking |
| O5 | Submit all assessment deliverables on time. | See Deliverables Calendar |

## Scope

In scope: 1-D axial, non-isothermal, adiabatic (Q_wall = 0); single-component CO₂/carrier gas; Toth isotherm with T-dependence; LDF kinetics; Python MOL + stiff integrator; OAT + one 2-parameter interaction.

Out of scope (deferred to FYP): wet-lab experiments, cyclic adsorption/regeneration, 2-D radial gradients, Ergun pressure drop, humidity co-adsorption, Bayesian inverse problems, optimal-transport analysis.

# Master Research Question & Sub-Hypotheses

How do superficial gas velocity, inlet CO₂ concentration, bed length, and adsorption temperature individually and jointly shape breakthrough time and stoichiometric utilisation of an amine-functionalised packed bed at DAC-relevant concentrations — and to what extent is this predicted from first principles by the Rankine–Hugoniot shock condition and the dimensionless groups (Pe, NTU, α)?

| H# | Topic | Hypothesis | Anchor source | Accept threshold |
| --- | --- | --- | --- | --- |
| H1 | Feed velocity / Pe | Higher u → shorter τ_BT; utilisation η drops as Pe increases. At high NTU, τ_BT ∝ 1/u. | Stampi-Bombelli 2024; Myers & Font 2020 | τ_BT ∝ u^(−0.9 to −1.1) verified |
| H2 | Inlet C_in | Higher C_in → shorter τ_BT; q_dyn roughly constant 400–2000 ppm (concave Toth isotherm). | Chen et al. 2023; Stampi-Bombelli 2024 | R-H chord within ±15% of v_front |
| H3 | Bed length L | τ_BT scales linearly with L; W_MTZ ∝ √(L/Pe); η independent of L at fixed NTU/length. | Myers & Font 2020 | τ_BT ∝ L, R²>0.97; MTZ within 20% |
| H4 | Temperature T_ads | Higher T_ads reduces q* via Toth b(T) → earlier breakthrough, tracking q*(T)/q*(25°C). | Stampi-Bombelli 2024; Jin et al. 2025 | Within ±20% of q* ratio |
| H5 | Front velocity | v_shock = u·ΔC / (ε·ΔC + (1−ε)·ρ_p·Δq) matches simulated shock speed. | Myers & Font 2020; LeVeque Ch.3 | ¦v_sim − v_RH¦/v_RH < 15% |

Each of H1–H5 gets its own Results subsection and an accept / refine / reject verdict in the Conclusions.

# Literature Anchor Map

The core literature-review tool. Seven anchor sources, each tagged by tier, the hypotheses it serves, and the week it first becomes load-bearing. Fill in the reading log the day you finish each paper.

Myers & Font (2020)

Int. J. Heat Mass Transfer, 163, 120434

Tier 1   •   Serves: H3, H5, Gate B   •   First referenced: Week 2

Used for: Analytical traveling-wave solution; Rankine–Hugoniot adsorption-shock formula; theoretical foundation for all front-velocity predictions.

☐ Read      ☐ Key equations extracted      ☐ Cited in report draft

| Key result / equation |  |
| --- | --- |
| Relevance to my model |  |
| Open questions |  |

Stampi-Bombelli et al. (2024)

Industrial & Engineering Chemistry Research — PRIMARY BENCHMARK

Tier 1   •   Serves: H1, H2, H4, Gate C   •   First referenced: Week 6

Used for: Breakthrough experiments at 400 ppm; Toth isotherm parameters (Table 2); PFO/dual-kinetic models; packed-bed geometry; capacity-vs-temperature data.

☐ Read      ☐ Key equations extracted      ☐ Cited in report draft

| Key result / equation |  |
| --- | --- |
| Relevance to my model |  |
| Open questions |  |

Chen et al. (2023)

Energy, 282

Tier 2   •   Serves: H1, H2   •   First referenced: Week 8

Used for: Breakthrough simulations at 500–2000 ppm; concentration effect on front dynamics and capture rate (mmen-Mg2(dobpdc) MOF, LDF kinetics); validates concentration-sweep direction.

☐ Read      ☐ Key equations extracted      ☐ Cited in report draft

| Key result / equation |  |
| --- | --- |
| Relevance to my model |  |
| Open questions |  |

Pedrozo et al. (2026)

Computers & Chemical Engineering, 204

Tier 2   •   Serves: H1, H3, H4   •   First referenced: Week 11

Used for: 1-D reactive transport model; TVSA cycle optimisation; 1-D vs 2-D cost comparison (~40×); template for cyclic Future-Work discussion.

☐ Read      ☐ Key equations extracted      ☐ Cited in report draft

| Key result / equation |  |
| --- | --- |
| Relevance to my model |  |
| Open questions |  |

de Joannis et al. (2025)

Carbon Capture Science & Technology, 17

Tier 2   •   Serves: H2, H4   •   First referenced: Week 13

Used for: Breakthrough under humid conditions; Lewatit sorbent; packed-bed vs monolith comparison at process scale; humidity as Future-Work driver.

☐ Read      ☐ Key equations extracted      ☐ Cited in report draft

| Key result / equation |  |
| --- | --- |
| Relevance to my model |  |
| Open questions |  |

Jin et al. (2025)

Renewable & Sustainable Energy Reviews, 217

Tier 2   •   Serves: H4   •   First referenced: Week 1

Used for: Comprehensive review of T and RH effects on amine sorbents (−20 to 40°C, 0–100% RH); validates direction of the T_ads effect; sorbent classification context.

☐ Read      ☐ Key equations extracted      ☐ Cited in report draft

| Key result / equation |  |
| --- | --- |
| Relevance to my model |  |
| Open questions |  |

Xu et al. (2024)

Energy Conversion and Management, 322

Tier 2   •   Serves: H2, fundamentals   •   First referenced: Week 1

Used for: DAC fundamentals review; adsorption kinetics and thermodynamics; system-design context for Introduction / Literature Review chapters.

☐ Read      ☐ Key equations extracted      ☐ Cited in report draft

| Key result / equation |  |
| --- | --- |
| Relevance to my model |  |
| Open questions |  |

Open item for supervisor meetings: if SUTD rig geometry becomes available (d_c, L, sorbent type, thermocouple positions), add as a model-vs-experiment stretch check in the Discussion — not blocking. Baseline uses Stampi-Bombelli 2024 literature parameters throughout.

# Prioritised Reading List

## Tier 1 — read in Week 1, referred to throughout

- Evans, PDE — Ch. 3 (first-order equations), in full.

- Myers & Font 2020, Int. J. Heat Mass Transf. 163, 120434 — analytical foundation.

- LeVeque, Numerical Methods for Conservation Laws — Ch. 3 (scalar laws), Ch. 6–7 (upwind).

- Ruthven, Principles of Adsorption and Adsorption Processes — Ch. 5 (breakthrough), Ch. 8 (thermal effects).

- Stampi-Bombelli et al. 2024, I&EC Research — primary benchmark.

## Tier 2 — reference when the topic arrives

- Chen et al. 2023, Energy 282 — concentration-range sweep context.

- Pedrozo et al. 2026, Comput. Chem. Eng. 204 — reactive transport model template.

- Jin et al. 2025, Renew. Sustain. Energy Rev. 217 — sorbent temperature sensitivity.

- de Joannis et al. 2025, Carbon Capture Sci. Tech. 17 — packed bed vs monolith; humidity context.

- Xu et al. 2024, Energy Convers. Manage. 322 — DAC fundamentals.

- Bird, Stewart & Lightfoot, Transport Phenomena — Ch. 6, 11, 14.

- Ascher & Petzold, Computer Methods for ODEs and DAEs.

## Tier 3 — enrichment (only if on-track; do not let these crowd out deliverables)

- Villani, Topics in Optimal Transport — Ch. 1.

- LeVeque, Numerical Methods for Conservation Laws — Ch. 14 (Riemann problems).

- Evans, PDE — Ch. 5 (Sobolev spaces), only if core project is on track.

# Mathematical Learning Track

Paired weekly with the technical work, so that the Final Report's mathematical chapter reads as a coherent exposition, not a parts catalog.

| Wk | Topic | Why it matters | Reading | Exercise |
| --- | --- | --- | --- | --- |
| 1 | Method of characteristics (linear 1st-order PDE) | Prerequisite for adsorption wave theory | Evans §3.1; Strauss §14.1 | Solve u_t + c(x)u_x = 0 for 3 choices of c(x); draw characteristics |
| 2 | R-H shock; traveling-wave substitution ξ = z−vt; self-sharpening for concave isotherms | Directly predicts τ_BT and v_front (H5, Gate B) | Myers & Font §2–3; LeVeque Ch.3 | Derive v_shock for Langmuir, then Toth; draw the chord on q*-vs-C |
| 3 | Buckingham Π theorem; scaling analysis | Universalises the parametric study | BSL Ch.6; Barenblatt, Scaling | Non-dimensionalise the 4-PDE system by hand |
| 4 | Method of lines; stiff ODE integration (BDF, LSODA) | Underpins the entire solver | Ascher & Petzold; scipy docs | Code the heat equation MOL; compare RK4 vs LSODA step counts |
| 5 | Upwind schemes; numerical diffusion; CFL | Wrong scheme fakes or smears shocks | LeVeque Ch.6–7 | Solve linear advection at CFL = 0.5, 1.0, 1.1; observe |
| 6 | Constant-pattern analysis (LUB/UB); MTZ width scaling | Explains self-sharpening front; needed for W_MTZ discussion | Ruthven Ch.8; Do Ch.3 | Show W_MTZ ∝ √(L/Pe) analytically for the dispersive case |
| 8 | Forward sensitivity equations | Lets you report ∂τ_BT/∂u as a number, not an eyeball | Cacuci, Sensitivity & Uncertainty Ch.1 | Hand-derive the sensitivity PDE for u; interpret sign |
| 11 | Local equilibrium limit; singular perturbation in NTU | Explains sharp- vs spread-front transition (H1/H3) | Ruthven Ch.8; Kevorkian & Cole | Show NTU→∞ collapses parabolic to hyperbolic; verify in sim |
| 12 | Breakthrough integration: τ_st, η = τ_st/τ_sat, q_dyn vs q_eq | Translates output into figures comparable to Stampi-Bombelli Table 3 | Stampi-Bombelli §3; Ruthven Ch.5 | Compute η and q_dyn from a synthetic C_out(t); check mass balance |
| 13 | Response-surface methodology; quadratic fits | Summarise 9 u×C_in runs as one function | Montgomery, DOE Ch.11 | Fit y = β₀+Σβᵢxᵢ+Σβᵢⱼxᵢxⱼ to synthetic data |
| 14 | Rescaling into (Pe, NTU, α); log-derivative ranking | Final universalisation step | Kuzmin; advanced transport texts | Rank ∂(log τ_BT)/∂(log Π) for each group |

# 18-Week Master Timeline

Condensed from the Study Plan, with active study-type tags per week. ◄ marks the current week.

| Wk | Dates | Phase | Types | Focus |
| --- | --- | --- | --- | --- |
| 1 | 20–24 Apr | P0 Kickoff | M T W | Characteristics + traveling-wave reading; install Python; read all 7 papers; LaTeX skeleton |
| 2 | 27 Apr–1 May | P1 Derivation | M T W | R-H shock & traveling-wave theory; derive 4-PDE system; set ICs/BCs |
| 3 | 4–8 May | P1 Non-dim | M T W D | Buckingham Π; identify Pe, NTU, α — Journal #1 due Mon 4 May |
| 4 | 11–15 May | P2 Linear solver | M T W G | MOL/stiff ODE theory; code linear advection-diffusion — Gate A: L²<1% |
| 5 | 18–22 May | P2 Nonlinear solver | M T W D | LDF/Toth/upwind theory; couple full 4-PDE system — Journal #2 due Mon 18 May |
| 6 | 25–29 May | P2 Benchmark + Interim draft | M T W G | Constant-pattern analysis; baseline sim vs Stampi-Bombelli; draft entire Interim — Gates B & C |
| 7 | 1–5 Jun | Interim gate | W D | Address validation gaps; submit Interim Report; Interim Review Wk 7–8 |
| 8 | 8–12 Jun | P3 Sensitivity 1 | M T W | Sensitivity equations; OAT sweep on u and C_in |
| 9–10 | 15–28 Jun | Term Break | — | Optional supplementary reading only; protect recovery time |
| 11 | 29 Jun–3 Jul | P3 Sensitivity 2 | M T W | Local equilibrium limit; OAT on L and T_ads ◄ you are here |
| 12 | 6–10 Jul | P4 Efficiency analysis | M T W | Breakthrough curve integration; post-process η and q_dyn |
| 13 | 13–17 Jul | P4 Interaction study | M T W D | Response-surface fitting; u×C_in 3×3 grid — Journal #3 due Mon 13 Jul |
| 14 | 20–24 Jul | P5 Dimensionless recast | M T W | Rescale into (Pe, NTU, α); rank parameters |
| 15 | 27–31 Jul | P6 Writing Sprint 1 | T W D | Clean code, figures ≥300dpi; draft Final Report v0.5 — Journal #4 due Mon 27 Jul |
| 16 | 3–7 Aug | P6 Writing Sprint 2 | T W | Rerun requested cells; Final Report v1.0, proofread |
| 17 | 10–14 Aug | P7 Submit + prep | W D | Submit Final Report Mon 10 Aug; build slide deck; 2 rehearsals |
| 18 | 17–19 Aug | P7 Defence | D | Final Presentation + panel Q&A |

Critical path: Wk 1 read → Wk 2–3 derive + non-dim → Wk 4 Gate A → Wk 5 Gate B → Wk 6 Gate C + interim draft → Wk 7 submit. If a Gate slips more than 3 days, re-baseline immediately — the term break has zero slack and Wk 15–16 are already writing-constrained. Buy back slippage by descoping sweep levels, not by working through the term break.

# Validation Gates

No parametric sweep starts until Gates A–C pass. This is the single most important rule in the schedule.

| Gate | Due | Tests | Method | Pass criterion |
| --- | --- | --- | --- | --- |
| Gate A | Wk 4 | Linear solver | ∂C/∂t + u∂C/∂z = D_ax∂²C/∂z², step inlet, zero adsorption, vs. Ogata–Banks analytical solution. | L² error < 1% on 200-node grid |
| Gate B | Wk 5–6 | Nonlinear front | Isothermal Toth + LDF; adsorption front velocity vs. R-H chord v_RH. | ¦v_sim − v_RH¦ / v_RH < 10% |
| Gate C | Wk 6 | Stampi-Bombelli benchmark | Full non-isothermal solver reproduces the 400 ppm breakthrough curve. | τ_BT within ±20% |

## Gate A workflow detail

- Run solver on linear advection-diffusion only.

- Compare against the Ogata–Banks analytical solution (step-input, semi-infinite column).

- Compute relative L² norm of pointwise difference across all z nodes at fixed t.

- Pass if < 1%. If not: grid too coarse or timestep too large — refine before adding nonlinear terms.

# Dimensionless Groups — Quick Reference

| Group | Definition | Typical range | Meaning |
| --- | --- | --- | --- |
| Pe | uL / D_ax | 10–500 | Convective vs dispersive transport; governs MTZ width |
| NTU | k_LDF a_p L (1−ε) / (εu) | 1–20 | Mass-transfer rate vs residence time; proximity to constant-pattern |
| Pe_h | ρ_g c_pg u L / λ_ax | 10–200 | Thermal convective vs conductive transport |
| α | ρ_p(1−ε)Δq / (εΔC) | 1–100 | Solid- vs gas-phase CO₂ capacity; sets v_shock / u |
| Λ | (−ΔH_ads)Δq / (c_pg T_ads) | 0.1–1 | Heat-of-adsorption feedback strength on temperature rise |

Pe, NTU, and α are the three most important groups for this study — they respectively govern MTZ dispersion, proximity to local equilibrium, and adsorption-shock speed relative to u.

# Deliverables & Assessment Calendar

| Wk | Deliverable | Due | Weight |
| --- | --- | --- | --- |
| 3 | Bi-weekly Journal #1 | Mon 4 May 2026 | 2.5% |
| 5 | Bi-weekly Journal #2 | Mon 18 May 2026 | 2.5% |
| 7 | Interim Report | Mon 1 Jun 2026 | 10% |
| 7–8 | Interim Review & Assessment | 1–5 Jun 2026 | 30% |
| 13 | Bi-weekly Journal #3 | Mon 13 Jul 2026 | 2.5% |
| 15 | Bi-weekly Journal #4 | Mon 27 Jul 2026 | 2.5% |
| 17 | Final Report | Mon 10 Aug 2026 | 10% |
| 18 | Final Assessment | 17–19 Aug 2026 | 30% |
| 18 | Final Presentation (panel) | 17–19 Aug 2026 | 10% |

60% of the grade sits in the two Assessment Files (Wk 7–8 and Wk 18), filled against the quality of journals, reports, and demonstrated understanding in meetings — the journal entries are leveraged at roughly 6× their nominal weight through that impression.

# Top Risks to Watch

| # | Risk | Impact | Response |
| --- | --- | --- | --- |
| R1 | Solver fails Gate A by Wk 4 | High | Drop to hand-coded Crank–Nicolson; consult Birgersson; 3-day buffer built in |
| R3 | Derivation chapter overrun → late Interim | Critical | Scope Interim to H1–H2 only; complete H3–H5 by Wk 13 |
| R5 | Scope creep into 2-D / humidity / cyclic sim | Medium | Part I §1.3 'Out of scope' is the answer; bookmark for FYP |
| R6 | Burnout in Wk 11–13 post term-break | Medium | Cut interaction grid to 2×3; call NP supervisor |
| R7 | Laptop / code-loss catastrophe | Catastrophic | Push every commit to GitHub nightly; weekly Drive backup of .npz results |

# Weekly Operating Rhythm

| Day | Block | Activity |
| --- | --- | --- |
| Mon | 09:00–10:30 | Math theory (Evans / LeVeque / Myers & Font) |
| Tue | 14:00–15:00 | Physical-chemistry reading (Ruthven / one anchor paper) |
| Wed | 10:00–12:00 | Coding sprint — one feature or validation gate per session |
| Thu | 14:00–15:00 | Literature: read one source end-to-end; add 3 lines to the annotated bibliography |
| Fri | 14:00–15:00 | Integration note — 400–600 words connecting the week's math to the week's code |
| Sat | 2–3 h | Extended coding/analysis (optional; skip without guilt during term break) |
| Sun | 30 min | Read next week's timeline row; draft Monday's journal opening |

Daily non-negotiables: 09:00 — read one page of the week's math anchor (15 min). End of day — commit code to GitHub with a meaningful message, even on non-coding days.

# Working Notes

Blank derivation / reading-session space for anything that doesn't fit neatly under a single paper or math-track week.

## Session 1

| Date / topic |  |
| --- | --- |
| Notes / derivation |  |

## Session 2

| Date / topic |  |
| --- | --- |
| Notes / derivation |  |

## Session 3

| Date / topic |  |
| --- | --- |
| Notes / derivation |  |

## Session 4

| Date / topic |  |
| --- | --- |
| Notes / derivation |  |